****

Leveraging ICT Product Innovations by Enhancing Codes of Modern Art

Project No. 1.1.1.2/VIAA/1/16/106

Time Diagram

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Diagram in quarters | | | | | | | | | | | | | | |
| **2017** | | **2018 2019 2020 2021** | | | | | | | | | | | | |
| Quarters | 1  sept | 2  oct-dec | 3  jan-march | 4  apr-june | 5  jul-sept | 6/2018  oct | 6/2019  oct-dec | 7  jan-march | 8  apr-june | 9  jul-sept | 10  oct-dec | 11  jan-march | 12  apr-june | 13  jul-aug | |
| Work package 1 (WP1). State-of-the art in the field of modernism codes and its intersection with ICT | *WP1* | ***WP1*** |  |  |  |  |  |  |  |  |  |  |  |  | |
| WP 2. In-depth interviews and their analysis |  | *WP2* | *WP2* | *WP2* | *WP2* | *WP2* | *WP2* | *WP2* | ***WP2*** |  |  |  |  |  | |
| WP 3. Delphi method of questioning experts | *WP3* | *WP3* | *WP3* | *WP3* | ***WP3*** |  |  |  |  |  |  |  |  |  | |
| WP 4. EKD modeling on new IT product creation |  |  |  | *WP4* | *WP4* | *WP4* | *WP4* | *WP4* | *WP4* | *WP4* | *WP4* | ***WP4*** |  |  | |
| WP 5. QFD method of measuring customer’s satisfaction |  |  |  |  | *WP5* | *WP5* | *WP5* | *WP5* | *WP5* | *WP5* | *WP5* | *WP5* | ***WP5*** |  | |
| WP 6. Study of Design science research methods | *WP6* | *WP6* | *WP6* | *WP6* | ***WP6*** |  |  |  |  |  |  |  |  |  | |
| WP 7. Conceptual design of product idea development roadmap |  |  |  |  |  |  | *WP7* | *WP7* | ***WP7*** |  |  |  |  |  | |
| WP 8. Concept of product prototype |  |  | *WP8* | *WP8* | ***WP8*** |  |  |  |  |  |  |  |  |  | |
| WP 9. Design of product prototype. Creative lab 1 |  |  | *WP9* | *WP9* | *WP9* | *WP9* | *WP9* | ***WP9*** |  |  |  |  |  |  | |
| WP 10. Ethics, privacy |  |  |  | *WP10* | *WP*  *10* | *WP10* | ***WP***  ***10*** |  |  |  |  |  |  |  | |
| WP 11. Experimental development of the ICT models/prototypes. Creative lab 2 |  |  |  |  |  |  |  |  | *WP*  *11* | *WP*  *11* | ***WP***  ***11*** |  |  |  | |
| WP 12. Update of the roadmap |  |  |  |  | ***WP12*** |  |  |  |  |  |  |  |  |  | |
| WP 13. Creation of TMA/ICT methodology |  |  |  |  |  |  |  |  | *WP 13* | *WP 13* | *WP*  *13* | ***WP***  ***13*** |  |  | |
| WP 14. Project management, coordination, monitoring |  |  |  |  |  |  |  |  |  |  |  |  | *WP*  *14* | ***WP***  ***14*** |  |
| Mobility (Mob) |  | ***Mob 24.10.2017*** |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publications (P1-3) |  |  |  |  |  |  |  | *P1* |  |  | *P2* |  | *P3* |  |  |
| Conferences (C1-2) |  |  | ***C1 17.03.***  ***2018*** |  |  |  |  |  |  |  |  |  | *C2* |  |  |
| Public engagement and dissemination of the project’s results (Dis) | ***Dis1.1***  ***29.09.***  ***2017*** | ***Dis***  ***1.2***  ***06.12.***  ***2017***  ***Dis2 24.10.***  ***2017***  ***Dis8 23.11.***  ***2017*** | ***Dis6***  ***17.03.***  ***2018 (C1)*** |  |  |  | *Dis10* | *Dis9* | *Dis2* |  | *Dis*  *11* |  | *Dis*  *13.1*  *13.2*  *13.3* |  |  |
| Milestones (M) and reports (R) |  | ***R1 19.01.***  ***2018*** | ***M6 17.03.***  ***2018 (C1)*** |  | ***R3, R8*** |  | *R4, R10* | *R5* |  |  |  |  |  | *R14* |  |

ViA HESPI director Agita Līviņa

28.09.2018.

Post-doctorate researcher Ieva Gintere

28.09.2018.